## Master plan
MASTER PLAN
No | Fearture Name | Days | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18
1 | UI LIBRARY | 50
2 | MU-BO-FO-Search Result | 30 | bar: Week 1 to Week 3
3 | UI LIBRARY - Media Picker | 10 | bar: MASTER PLAN Week 4
4 | PRODUCT DETAIL | 30 | bar: MASTER PLAN Week 5 to MASTER PLAN Week 10
5 | PRODUCT FORM | 30 | bar: MASTER PLAN Week 5 to MASTER PLAN Week 10
6 | SEARCH BAR | 10 | bar: MASTER PLAN Week 11
7 | HIGHT LIGHT - EVENT SERIES | 10 | bar: MASTER PLAN Week 12
8 | RECEIVE SELL - EVENT SERIES | 9 | bar: MASTER PLAN Week 13
9 | PRODUCT COMPARE - EVENT SERIES | 10 | bar: MASTER PLAN Week 14
10 | ON BOARDING | 4 | bar: MASTER PLAN Week 15
11 | BROCKER LIST PAGE | 40 | bar: Week 1 to MASTER PLAN Week 4
12 | UI LIBRARY - Maps | 10 | bar: MASTER PLAN Week 5
13 | CUSTOMER LIST PAGE | 30 | bar: MASTER PLAN Week 6 to MASTER PLAN Week 8
14 | CONTACT / ADVISE PAGE | 8 | bar: MASTER PLAN Week 9
15 | REGISTER/LOGIN PAGE | 16 | bar: MASTER PLAN Week 10 to MASTER PLAN Week 11
16 | ACCOUNT PAGE | 27 | bar: MASTER PLAN Week 12 to MASTER PLAN Week 14
17 | SHARING - EVENT SERIES | 13 | bar: MASTER PLAN Week 15
18 | NOTIFICATION | 13 | bar: MASTER PLAN Week 16
|  |  |  | Team 1 |  |  |  |  | Throughout the time of project implementation
|  |  |  | Team 2 |  |  |  |  | FINAL TEST AND FIX BUGS
|  |  | Start day | 03/06/2019
|  |  | End day | 2019-12-10

## Front end Developer library
ReactJs
GraphQL
Apollo-GraphQL

## Front-end Solution Architecture
Back end
API
Gateway
LIGHT-SERVER

## Organization Chart
Front-End
DinhBB (Lead)
Team 1
DuyNK (Lead)
Team 2
PhuongTA (Lead)
DungTPQ (Dev)
LongTT (Dev)
CuongLD (Dev)