## Home
ECOE app Feature 1 Estimation Breakdown V1.0 - ECOE
Estimate Totals man days | 385
Estimate Start date
Total Members | 6
Team 1 | Mr Duy (Lead), Mr Dũng
Team 2 | Mr Phương (Lead), Mr Long
Team 3 | Mr Cường, ?... (support data interagtion)

## BO-SD-FO
Feature 1 Estimation Breakdown V1.0 - ECOE
109
Code | Feature | Description | Duration (days) | Start | Finish | Priority | Staff | Staff backup | Done | Mr.Duy | Medium
1 | UI LIBRARY |  | 63 | [6 empty] | Mr.Long | Height
1.1 | Element |  | 26 | [6 empty] | Mr.Phương | Urgent
1.1.1 | Check box |  | 2 |  |  |  | Mr.Dũng |  |  | Mr.Dũng | Low
1.1.2 | Icons |  | 2
1.1.3 | Tables |  | 1
1.1.4 | Forms |  | 1
1.1.5 | Dropdown |  | 1
1.1.6 | Toast Notifications |  | 2
1.1.7 | Toogles |  | 1
1.1.8 | Search Bar |  | 1
| Search Bar Mobile |  | 2
1.1.9 | Tabs |  | 1
1.1.10 | Tags |  | 2
1.1.11 | Buttons |  | 3
1.1.12 | Avatars |  | 3
1.1.13 | Sliders & Chervon |  | 3
1.1.14 | Overlay |  | 1
1.2 | Globals component |  | 37
1.2.1 | Filters |  | 10
1.2.2 | Maps |  | 10
1.2.3 | Progress trackers |  | 2
1.2.4 | Cards |  | 5
1.2.5 | Footer |  | 1
1.2.6 | Navigation |  | 2
| Navigation mobile |  | 2
1.2.7 | Media Picker |  | 5 |  |  |  | Mr.Phương
2 | RESULT PAGE |  | 17
2.1 | UI design |  | 12
| Scroll inifite |  | 1
| Grid View |  | 1
| Grid View Mobile |  | 1
| Grid List |  | 1
| Grid List Mobile |  | 1
| Sort/Toggle bar |  | 1
| Search Critical session |  | 1
| Like - result page |  | 2
| Maps |  | 1
| Mobile |  | 2
2.2 | Intergration client-server |  | 5
2.2.1 | Server |  | 3
2.2.1.1 | Product Search |  | 3
- Context search
- Filter search
- Session search
- Region search
- Hide
2.2.2 | Client |  | 2
2.2.2.1 | Product Search |  | 2
2.2.2.2 | - Context search
2.2.2.3 | - Filter search
2.2.2.4 | - Session search
2.2.2.5 | - Region search
3 | BO-MS (MUTUAL SPACE) PAGE |  | 14
3.1 | UI design |  | 10
| Banner |  | 0.5
| Search Bar |  | 0.5
| Session Scroll |  | 1
| S1: Mới Nhất |  | 0.5
| S2: Nổi Bật |  | 1
| S3: Từ ECOE |  | 1
| S4: Khu Vực Sôi Động |  | 1
| S5: Dành Cho Bạn |  | 0.5
| S6: Xem Gần Đây |  | 1
| Danh sách yêu thích |  | 1
| Mobile |  | 2
3.2 | Intergration client-server |  | 4
3.2.1 | Server |  | 2
3.2.1.1 | Product Search |  | 2
3.2.1.2 | - Mới Nhất
3.2.1.3 | - Nổi Bật
3.2.1.4 | - Từ ECOE
3.2.1.5 | - Khu Vực sôi động
3.2.1.6 | - Dành cho bạn
- Xem Gần đây
3.2.2 | Client |  | 2
| Product Search |  | 2
- Mới Nhất
- Nổi Bật
- Từ ECOE
- Khu Vực sôi động
- Dành cho bạn
- Xem Gần đây
4 | BO-SD (SUB-DOMAIN) PAGE |  | 7
4.1 | UI design |  | 5
| Banner |  | 0.5
| Nổi bật |  | 1
| Sản phẩm khác |  | 1
| Đã ẩn |  | 0.5
| Mobile |  | 2
4.2 | Intergration client-server |  | 2
4.2.1 | Server |  | 1
4.2.1.1 | Product search |  | 1
4.2.1.2 | - Nổi Bật
4.2.1.3 | - Ẩn
4.2.2 | Client |  | 1
| Product search |  | 1
- Nổi Bật
- Ẩn
5 | FO-SD (FRONT OFFICE SUB-DOMAIN) PAGE |  | 8
5.1 | UI design |  | 4
| Banner |  | 0.5
| Nổi bật |  | 0.5
| Đang trưng bày |  | 0.5
| Xem gần đây |  | 0.5
| Session Scroll |  | 1
| Mobile |  | 1
5.2 | Intergration client-server |  | 4
5.2.1 | Server |  | 2
5.2.1.1 | Product search |  | 2
5.2.1.2 | - Nổi Bật
5.2.1.3 | - Đang trưng bày
5.2.1.4 | - Xem Gần đây
5.2.2 | Client |  | 2
| Product search |  | 2
- Nổi Bật
- Đang trưng bày
- Xem Gần đây
7.2.1 | Server
7.2.1.1
7.2.1.2
7.2.1.3
7.2.1.4
7.2.1.5
7.2.1.6
7.2.2 | Client
8.2.1 | Server
8.2.1.1
8.2.1.2
8.2.1.3
8.2.1.4
8.2.1.5
8.2.1.6
8.2.2 | Client

## Liên hệ-Tư vấn mua
Feature 1 Estimation Breakdown V1.0 - ECOE
8
Code | Feature | Description | Duration (days) | Start | Finish | Priority | Staff | Staff backup | Done | Mr.Duy | Medium
1 | CONTACT / ADVISE PAGE |  | 8
1.1 | UI design |  | 5
| Product Card |  | 1
| Contact form |  | 0.5
| Customer info |  | 2
| Contact/Advise form |  | 0.5
| Mobile |  | 1
1.2 | Intergration client-server |  | 3
1.2.1 | Server |  | 2
| Product Card info |  | 1
| Add Customer info |  | 1
1.2.2 | Client |  | 1
| Product Card info |  | 0.5
| Add Customer info |  | 0.5

## Chia sẽ-Nhận Bán-Nổi bật-Compar
Feature 1 Estimation Breakdown V1.0 - ECOE
42
Code | Feature | Description | Duration (days) | Start | Finish | Priority | Staff | Staff backup | Done | Mr.Duy | Medium
1 | SHARING - EVENT SERIES |  | 13
1.1 | UI design |  | 7
| Brocker Info card |  | 1
| Search Text |  | 0.5
| Brocker listing | Group Brocker and listing | 2
| Popup |  | 0.5
| Check & uncheck bar |  | 1
| Mobile |  | 2
1.2 | Intergration client-server |  | 6
1.2.1 | Server |  | 3.5
| Brocker listing | Check, uncheck | 1
| Search by text |  | 1
| Save | save sharing listing, (check or uncheck) | 1
| Unsharing |  | 0.5
1.2.2 | Client |  | 2.5
| Binding data |  | 1
| Search by text |  | 0.5
| Save |  | 0.5
| Unsharing |  | 0.5
2 | RECEIVE SELL - EVENT SERIES |  | 9
2.1 | UI design |  | 3
| Brocker Card |  | 1
| Popup listing |  | 1
| Mobile |  | 1
2.2 | Intergration client-server |  | 6
2.2.1 | Server |  | 3
| Listing Broker |  | 1
| Receive sell |  | 1
| Cancel receive sell |  | 1
2.2.2 | Client |  | 3
| Listing Broker |  | 1
| Receive sell |  | 1
| Cancel receive sell |  | 1
2 | HIGHT LIGHT - EVENT SERIES |  | 10
2.1 | UI design |  | 5
| Popup search product | Create popup modal with search bar and grid view listing | 1
| Selecting Grid | Grid with check box all, and checkbox in each item | 1
| Search bar | Autocomplete search | 1
| Sorting | Sorting popup | 1
| Mobile |  | 1
2.2 | Intergration client-server |  | 5
2.2.1 | Server |  | 2.5
| Search product | Search product | 1
| Save hightligh product | Save list of product's hightlight | 1
| Delete highlight product | Delete list of product's hightlight | 0.5
2.2.2 | Client |  | 2.5
| Search product | Binding list with grid | 1
| Save hightligh product | Save and redirect to BO-SD | 1
| Delete highlight product | Delete and reload page | 0.5
2 | PRODUCT COMPARE - EVENT SERIES |  | 10
2.1 | UI design |  | 8
| Map |  | 1
| Project Info card |  | 1
| Home info card |  | 1
| Grid |  | 0.5
| Search location |  | 0.5
| Drawing and calculating time |  | 1
| Mini popup | Collapse/ expand. Add, remove | 1
| Mobile | Grid => tab Panel | 2
2.2 | Intergration client-server |  | 2
2.2.1 | Server |  | 1
| Get Compare list |  | 1
2.2.2 | Client |  | 1
| Binding list |  | 1

## Thông tin dự án
Feature 1 Estimation Breakdown V1.0 - ECOE
29
Code | Feature | Description | Duration (days) | Start | Finish | Priority | Staff | Staff backup | Done | Mr.Duy | Medium
1 | PRODUCT DETAIL |  | 29
1.1 | UI design |  | 19.5
| Section1: Overview | Common info, carousel, 3d, 360, street view
| Section 2: Outstanding advancetages |  | 1
| Section 3: project- tax, fee info |  | 0.5
| Section 4: project - type info | department, villa, house, land | 2
| Section 5: Position |  | 2
| Section 6: Project- internal facilities |  | 0.5
| Section 7: project - investor |  | 1
| Section 8: project - cooperation unit |  | 1
| Section 9: department - infrastructure |  | 1.5
| Section 10: department - Project short info |  | 0.5
| Section 11: loan estimates |  | 3
| Section 12: the similar product |  | 0.5
| Detail page | Auto switch contain between project, land, home | 1
| Mobile |  | 5
1.2 | Intergration client-server |  | 9.5
1.2.1 | Server |  | 2
| Get Product detail |  | 2
1.2.2 | Client |  | 7.5
| Section1: Overview |  | 2
| Section 2: Outstanding advancetages |  | 0.5
| Section 3: project- tax, fee info |  | 0.5
| Section 4: project - type info |  | 0.5
| Section 5: Position |  | 0.5
| Section 6: Project- internal facilities |  | 0.5
| Section 7: project - investor |  | 0.5
| Section 8: project - cooperation unit |  | 0.5
| Section 9: department - infrastructure |  | 0.5
| Section 10: department - Project short info |  | 0.5
| Section 11: loan estimates |  | 0.5
| Section 12: the similar product |  | 0.5

## Đăng bài
Feature 1 Estimation Breakdown V1.0 - ECOE
46
Code | Feature | Description | Duration (days) | Start | Finish | Priority | Staff | Staff backup | Done | Mr.Duy | Medium
1 | PRODUCT FORM |  | 46
1.1 | UI design |  | 31.5
| Form Post | Breadcrum with previous button | 1
| Product Name | Autocomplete search, suggest product list (in case Project) | 2
| - Project Introduce |  | 1
| - Home Introduce |  | 1
| Price and Commission |  | 1
- Project Price/Comission
- Home Price/Comission
| Images |  | 2
| - Cover images | Upload file
| - Overview | Media picker
| - Floor plan | Media picker
| - Position | Media picker
| - Sample house | Media picker
| - Video | link
| - 3D | link
| - Street view | link
| - 360d | link
Information detail
| - Overview |  | 1
| - Outstanding advantages | Auto add other Outstanding advantages | 2
| - Position | Postion, hospital, school, market, other | 2
| - Infrastructure | Furniture, internal facilities | 1
| - Project information |  | 2
- Project type config
| + Department |  | 3
| + Villa |  | 1.5
| + Home |  | 1.5
| + Land |  | 1.5
| - Investor | Investor, Projects, documents, banks support | 3
| Mobile |  | 5
1.2 | Intergration client-server |  | 14.5
1.2.1 | Server |  | 8
| Config value data | Get all reference config data to fill all drop down component | 3
| Add Product |  | 2
| Edit Product |  | 2
| Get Product detail | Get product detail when update Product | 1
1.2.2 | Client |  | 6.5
| Get config value | Get reference config data and process relation behavior | 2
| Get Product detail | Get from server or get from local storage | 2
| Add Product |  | 1
| Insert product to local storage | Insert current product (not yet complete) to local storage | 0.5
| Edit product |  | 1

## Register-Login
Feature 1 Estimation Breakdown V1.0 - ECOE
16
Code | Feature | Description | Duration (days) | Start | Finish | Priority | Staff | Staff backup | Done | Mr.Duy | Medium
1 | REGISTER/LOGIN PAGE |  | 16
1.1 | UI design |  | 9.5
| Popup modal | Popup modal with progress bar | 1
| Register info | Facebook/Google/Zalo, phone, pass, veryfy pass | 2
| SMS verify | Input and receive new sms code | 0.5
| Contact Info | Veryfy email | 0.5
| Web domain | Veryfy sub-domain | 0.5
| Susscess page | Link to redirect sub-domain page | 0.5
| Login page |  | 1
| New password popup modal | Verify by SMS code | 0.5
| Register new pass popup |  | 0.5
| Register success Popup |  | 0.5
| Mobile |  | 2
1.2 | Intergration client-server |  | 6.5
1.2.1 | Server |  | 3.5
| Register account | Save new account with short information | 1
| Verify email | Check email is valid | 0.5
| Send sms code | Send and check sms code | 0.5
| Verify subdomain account | Check account is already exist | 0.5
| Login | Login API | 0.5
| Remeber account | Remeber account for next login | 0.5
1.2.2 | Client |  | 3
| Register account |  | 1
| Login | Login and store account information to local storage | 1
| Verify email, domain, sms code |  | 1

## Search Tổng
Feature 1 Estimation Breakdown V1.0 - ECOE
7
Code | Feature | Description | Duration (days) | Start | Finish | Priority | Staff | Staff backup | Done | Mr.Duy | Medium
1 | SEARCH BAR |  | 7
1.1 | UI design |  | 3.5
| Search component |  | 0.5
| Popup modal |  | 2
- Hint bar
- Filter bar
- Result bar
| Mobile |  | 1
1.2 | Intergration client-server |  | 3.5
1.2.1 | Server |  | 2
| Content search |  | 2
1.2.2 | Client |  | 1.5
| Async load data |  | 1
| Binding popup bar |  | 0.5

## OnBoarding
Feature 1 Estimation Breakdown V1.0 - ECOE
3.5
Code | Feature | Description | Duration (days) | Start | Finish | Priority | Staff | Staff backup | Done | Mr.Duy | Medium
1 | ON BOARDING |  | 3.5
1.1 | UI design |  | 3.5
| BO-SD | Sub domain - back office | 0.5
| Footer notifycation |  | 0.5
| FO-SD | Sub domain - front office | 0.5
| Post Product |  | 0.5
| Customer listing |  | 0.5
| Mobile |  | 1
1.2 | Intergration client-server |  | 0
1.2.1 | Server |  | 0
1.2.2 | Client |  | 0

## Email template
Feature 1 Estimation Breakdown V1.0 - ECOE
0
Code | Feature | Description | Duration (days) | Start | Finish | Priority | Staff | Staff backup | Done | Mr.Duy | Medium
1 | EMAIL TEMPLATE |  | 0
1.1 | UI design |  | 0
1.2 | Intergration client-server |  | 0
1.2.1 | Server |  | 0
1.2.2 | Client |  | 0

## Thông báo
Feature 1 Estimation Breakdown V1.0 - ECOE
13
Code | Feature | Description | Duration (days) | Start | Finish | Priority | Staff | Staff backup | Done | Mr.Duy | Medium
1 | NOTIFICATION |  | 13
1.1 | UI design |  | 6.5
| Notification list | Change color when read/unread | 1
| Search List | Autocomplete search | 1
| Scroll infinite | Pagination load when scroll | 1
| Brocker Card | With button add to Customer List | 1
| Setting page |  | 1
| Tab panel |  | 0.5
| Mobile |  | 1
1.2 | Intergration client-server |  | 6.5
1.2.1 | Server |  | 3.5
| List notification | Get list of notification of current user | 1
| Add to customer list | Add brocker to current user' customer list | 1
| Mark as Read/ all Read | Mark read for list of notification | 0.5
| Delete | Delete list of notification | 0.5
| Save setting | Save Notification setting | 0.5
1.2.2 | Client |  | 3
| List notification | Binding list notification, refetch query when scroll | 1
| Add to customer list | Implement action add customer | 0.5
| Mark as Read/ all Read | Click each notification or click all for mark unread | 0.5
| Delete |  | 0.5
| Save setting |  | 0.5

## Tài khoản
Feature 1 Estimation Breakdown V1.0 - ECOE
26.5
Code | Feature | Description | Duration (days) | Start | Finish | Priority | Staff | Staff backup | Done | Mr.Duy | Medium
1 | ACCOUNT PAGE |  | 26.5
1.1 | UI design |  | 15.5
| Broker info |  | 0.5
| Personal Card |  | 1
| - Personal Card Edit |  | 1
| - Veryfy info |  | 1
| - Upload Avatar |  | 1
| Career Card |  | 0.5
| - Career Card Edit |  | 1
| Other Card |  | 0.5
| - Other Card Edit |  | 1
| Personalized |  | 2
Change password
| Link Facebook |  | 1
| Link Google |  | 1
| Link Zalo |  | 1
| Mobile |  | 3
1.2 | Intergration client-server |  | 11
1.2.1 | Server |  | 5
| - Personal Card Detail/Update |  | 1
| - Veryfy info |  | 1
| - Upload Avatar |  | 1
| Career Card |  | 0.5
| - Career Card Edit |  | 0.5
| Other Card |  | 0.5
| - Other Card Edit |  | 0.5
1.2.2 | Client |  | 6
| - Personal Card Detail/Update |  | 1
| - Veryfy info |  | 1
| - Upload Avatar |  | 1
| Career Card - load |  | 0.5
| - Career Card - update |  | 0.5
| Other Card - load |  | 0.5
| - Other Card - update |  | 0.5

## Quản lý danh bạ
Feature 1 Estimation Breakdown V1.0 - ECOE
85
Code | Feature | Description | Duration (days) | Start | Finish | Priority | Staff | Staff backup | Done | Mr.Duy | Medium
9 | BROCKER LIST PAGE |  | 55
9.1 | UI design |  | 34
9.1.1 | Left Menu |  | 1
9.1.2 | Listing | with scroll infinite | 1
9.1.3 | Brocker Card |  | 5
9.1.4 | Sorting |  | 1
9.1.5 | Project Card |  | 2
9.1.6 | History listing page |  | 3
9.1.7 | Searching bar |  | 4
9.1.8 | Popup add brocker |  | 1
9.1.8.1 | - Brocker mini card |  | 1
9.1.8.2 | - Listing page |  | 2
9.1.8.3 | - Brocker Search |  | 1
9.1.9 | Group Card |  | 5
9.1.10 | Popup add brocker group |  | 2
9.1.10.1 | - Popup right bar |  | 1
| Mobile |  | 4
9.2 | Intergration client-server |  | 21
9.2.1 | Server |  | 13
9.2.1.1 | Brocker Listing |  | 2
9.2.1.2 | Group Listing |  | 2
9.2.1.3 | History listing |  | 2
| Brocker Detail |  | 0.5
| Group detail |  | 0.5
9.2.1.4 | Insert/Update/Delete Brocker |  | 2
9.2.1.5 | Insert/Update/Delete Group |  | 2
9.2.1.6 | Insert/Update/Delete History |  | 2
9.2.2 | Client |  | 8
| Brocker Listing |  | 1
| Group Listing |  | 1
| History listing |  | 1
| Brocker Detail |  | 1
| Group detail |  | 1
| Insert/Update/Delete Brocker |  | 1
| Insert/Update/Delete Group |  | 1
| Insert/Update/Delete History |  | 1
10 | CUSTOMER LIST PAGE |  | 30
10.1 | UI design |  | 14
| Customer Card |  | 1
| Sorting |  | 1
| Listing | With scroll infinite | 1
| Result Popup | Mutual space and subdomain | 2
| Searching bar |  | 1
| Popup add customer |  | 1
| - Advisory History mini card |  | 0.5
| - Advisory History Listing |  | 1
| - Customer Info |  | 1
| - SearchCritical Info |  | 1
| Popup Brocker Info |  | 1
| Popup alias name |  | 0.5
| Mobile |  | 2
10.2 | Intergration client-server |  | 16
10.2.1 | Server |  | 5
10.2.1.1 | Customer Listing |  | 1
10.2.1.2 | Advisory History Listing |  | 1
10.2.1.3 | Customer Detail |  | 0.5
10.2.1.4 | Customer Search Critical |  | 0.5
10.2.1.5 | Customer Insert/Delete/Update |  | 1
10.2.1.6 | Advisory Insert/Update/Delete |  | 1
10.2.2 | Client |  | 11
| Brocker Listing |  | 1
| Group Listing |  | 1
| History listing |  | 1
| Brocker Detail |  | 1
| Group detail |  | 1
| Insert/Update/Delete Brocker |  | 2
| Insert/Update/Delete Group |  | 2
| Insert/Update/Delete History |  | 2